## Timeline
Milestones | Specific | Due Date | Completion Date | Status | Roles & Responsibility
Research/ Resource Collection | Ideas for Design (framework) | 2020-05-11 |  | Completed | Team | https://bit.ly/2SZJdiU
| Key Activities | 2020-05-18 |  | Completed | Lobsang & Paljor
| Pictures | 2020-05-18 |  | Active | Lobsang & Paljor
| Financial Data | 2020-05-18 |  | Active | Paljor
Sort & Filter (Collected Data) | Filtering Data | 2020-05-25 |  | Active | Lobsang
| Content Evaluation | 2020-05-25 |  | Active | Lobsang
Visual & Graphics Creating | Infographics | 2020-05-25 |  | Active | Paljor
| Graphs and Tables | 2020-05-25 |  |  | Paljor
1st Draft | Consolidation | 2020-05-28 |  |  | Lobsang & Paljor
| Edits | 2020-06-04 |  |  | Lobsang & Paljor
| Review | 2020-06-04 |  |  | Kaydor La & Norsang La
2nd Draft | Edits | 2020-06-11 |  |  | Team
| Review | 2020-06-11 |  |  | Kaydor La & Norsang La
3rd Draft (if needed) | Edits
Review
Design (Final Draft) | Designing Framework & Review | 2020-06-25 |  |  | Team
| Completion | 2020-06-26 |  |  | Paljor
Printing | Start | 2020-06-29
| Completion | 2020-07-03

## Data
Donors | Source
USAID | Tashi Wangdue La
PRM | Tenzin Lodhen La
SOIIR | Jigme Yangchen La
EU | Nyima Yangzom La
FNF | Jigme Yangchen La